## Cost Data
Division | 2
| 01 00 00 | General Requirements
| 01 11 00 | Preconstruction Costs | 0
| 01 31 00 | Project Management and Coordination | 165000
| 01 41 00 | Permits | 3000
| 01 45 00 | Quality Control | 8000
| 01 51 00 | Temporary Utilities | 15000
| 01 52 00 | Construction Facilities | 35468.0789
| 01 54 00 | Construction Aids | 203313.0434
| 01 56 00 | Temporary Barriers & Enclosures | 25000
| 01 74 00 | Cleaning & Waste Management | 54500
Division | 2
| 02 00 00 | Existing Conditions
| 02 41 00 | Demolition | 0
| 02 82 00 | Asbestos Remediation | 0
| 02 83 00 | Trenching | 0
Division | 3
| 03 00 00 | Concrete
| 03 11 00 | Concrete Forming | 302400
| 03 20 00 | Concrete Reinforcing | 0
| 03 30 00 | Cast-in-Place Concrete | 177795.8609
| 03 35 00 | Concrete Finishing | 44527
| 03 40 00 | Precast Concrete | 77850
| 03 60 00 | Grouting | 68035
Division | 4
| 04 00 00 | Masonry
| 04 20 00 | Unit Masonry | 140360
| 04 43 00 | Stone Masonry | 0
Division | 5
| 05 00 00 | Metals
| 05 12 00 | Structural Steel Framing | 141400
| 05 20 00 | Metal Joists | 0
| 05 30 00 | Metal Decking | 0
| 05 51 00 | Metal Stairs | 0
| 05 52 00 | Metal Railings | 73570
| 05 59 00 | Metal Specialties | 0
Division | 6
| 06 00 00 | Wood, Plastics, and Composites
| 06 11 00 | Framing | 571330
| 06 20 00 | Finish Carpentry | 1261823.66
| 06 22 00 | Millwork | 425900
| 06 41 00 | Architechtural Wood Casework | 0
| 06 42 00 | Wood Paneling | 0
| 06 43 00 | Wood Stairs and Railings | 0
| 06 46 00 | Wood Trim | 315803.8944
| 06 48 00 | Wood Frames | 0
Division | 7
| 07 00 00 | Thermal and Moisture Protection
| 07 21 00 | Thermal Insulation | 237835
| 07 24 00 | EIFS | 271678.014
| 07 31 00 | Shingles | 81750
| 07 42 00 | Wall Panels | 0
| 07 46 00 | Siding | 561708
| 07 52 00 | Modified Bituminous Membrane Roofing | 0
| 07 53 00 | Elastomeric Membrane Roofing | 0
| 07 62 00 | Sheet Metal Flashing and Trim | 0
| 07 63 00 | Sheet Metal Roofing Specialties | 0
| 07 64 00 | Sheet Metal Wall Cladding | 0
| 07 72 00 | Roof Accessories | 0
| 07 81 00 | Applied Fireproofing | 26550
| 07 90 00 | Joint Protection | 0
Division | 8
| 08 00 00 | Openings
| 08 11 00 | Metal Doors and Frames | 89875
| 08 14 00 | Wood Doors | 0
| 08 31 00 | Access Doors and Panels | 8000
| 08 32 00 | Sliding Gates | 0
| 08 33 00 | Coiling Doors and Drilles | 10984.51
| 08 34 00 | Special Function Doors | 0
| 08 38 00 | Traffic Doors | 0
| 08 41 00 | Entrances and Storefronts | 39425
| 08 44 00 | Curtain Wall and Glazed Assemblies | 0
| 08 50 00 | Windows | 126145.3
| 08 70 00 | Hardware | 0
| 08 81 00 | Glass Glazing | 0
| 08 83 00 | Mirrors | 0
| 08 87 00 | Glazing Surface Films | 0
| 08 91 00 | Louvers | 0
Division | 9
| 09 00 00 | Finishes
| 09 20 00 | Plaster and Gypsum Board | 1139222
| 09 30 00 | Tiling | 0
| 09 50 00 | Ceiling | 0
| 09 60 00 | Flooring | 411100
| 09 72 00 | Wall Coverings | 0
| 09 91 00 | Painting | 197003
Division | 10
| 10 00 00 | Specialties
| 10 11 00 | Visual Display Units | 0
| 10 14 00 | Signage | 10950
| 10 20 00 | Interior Specialties | 11989.39
| 10 44 00 | Fire Protection Specialties | 0
| 10 51 00 | Lockers | 31062.37
| 10 57 00 | Wardrobe and Closet Specialties | 32532
| 10 70 00 | Exterior Specialties | 1640
Division | 11
| 11 00 00 | Equipment
| 11 11 00 | Vehicle Service Equipment | 0
| 11 13 00 | Loading Dock Equipment | 0
| 11 30 00 | Residential Equipment | 200600
| 11 41 00 | Food Storage Equipment | 0
| 11 48 00 | Food service Cleaning and Disposal Equipment | 0
| 11 52 00 | Audio-Visual Equipment | 0
| 11 53 00 | Laboratory Equipment | 0
Division | 12
| 12 00 00 | Furnishings
| 12 20 00 | Window Treatments | 0
| 12 21 00 | Window Blinds | 41300
| 12 30 00 | Casework | 0
| 12 32 00 | Manufactured Wood Casework | 0
| 12 35 00 | Specialty Casework | 0
| 12 36 00 | Countertops | 0
Division | 13
| 13 00 00 | Special Construction
Division | 14
| 14 00 00 | Conveying Equipment
| 14 20 00 | Elevators | 0
| 14 40 00 | Lifts | 0
| 14 42 00 | Wheelchair Lifts | 0
Division | 21
| 21 00 00 | Fire Suppression
| 21 10 00 | Water-Based Fire-Suppression System | 212000
Division | 22
| 22 00 00 | Plumbing
| 22 10 00 | Plumbing Piping | 674850
| 22 30 00 | Plumbing Equipment | 0
| 22 40 00 | Plumbing Fixtures | 0
| 22 42 00 | Commercial Plumbing Fixtures | 0
| 22 45 00 | Emergency Plumbing Fixtures | 0
| 22 47 00 | Drinking Fountains and Water Coolers | 0
Division | 23
| 23 00 00 | Heating, Ventilating, and Air Conditioning
| 23 07 00 | HVAC Insulation | 467650
| 23 08 00 | Commissioning of HVAC | 0
| 23 09 00 | Instrumentation and Control for HVAC | 0
| 23 10 00 | Facility Fuel System | 0
| 23 13 00 | Facility Fuel Storage | 0
| 23 20 00 | HVAC Piping and Pumps | 0
| 23 23 00 | Refrigerant Piping | 0
| 23 30 00 | HVAC Air Distribution | 0
| 23 70 00 | Central HVAC Equipment | 0
| 23 83 00 | Radiant Heating Units | 0
Division | 25
| 25 00 00 | Integrated Automation
Division | 26
| 26 00 00 | Electrical
| 26 09 00 | Instrumentation and Controls for Electrical Systems | 770000
| 26 10 00 | Medium-Voltage Electrical Distribution | 0
| 26 50 00 | Lighting | 52897
Division | 27
| 27 00 00 | Communications
| 27 10 00 | Structured Cabling | 0
| 27 20 00 | Data Communications | 0
| 27 30 00 | Voice Communications | 0
| 27 40 00 | Audio-Voice Communications | 0
| 27 50 00 | Distributed Communications and Monitoring Systems | 0
Division | 28
| 28 00 00 | Electronic Safety and Security
| 28 10 00 | Access Control | 0
| 28 20 00 | Video Surveillance | 0
| 28 30 00 | Security Detection, Aarm, and Monitoring | 0
| 28 40 00 | Life Safety | 0
Division | 31
| 31 00 00 | Earthwork
| 31 10 00 | Site Clearing | 0
| 31 20 00 | Earth Moving | 268300
| 31 37 00 | Riprap | 0
| 31 70 00 | Tunneling | 0
Division | 32
| 32 00 00 | Exterior Improvements
| 32 10 00 | Bases, Ballasts, and Paving | 53250
| 32 16 00 | Curbs, Gutters, Sidewalks, and Driveways | 28809.84
| 32 17 00 | Paving Specialties | 960
| 32 30 00 | Site Improvements | 16800
| 32 90 00 | Planting | 51251.17
Division | 33
| 33 00 00 | Utilities
| 33 10 00 | Water Utilities | 0
| 33 30 00 | Sanitary Sewerage | 0
| 33 70 00 | Electrical Utilities | 0

## Cost Report
Division | Sub - Division | Discription | Cost
01 00 00 |  | General Requirements | 584281.1223
01 11 00 |  | Preconstruction Costs | 0
01 31 00 |  | Project Management and Coordination | 165000
01 31 00 | 01 31 01 | Senior Construction Manager | 0
01 31 00 | 01 31 02 | Senior Estimator | 0
01 31 00 | 01 31 03 | Senior Project Manager | 0
01 31 00 | 01 31 04 | Project Coordinator | 0
01 31 00 | 01 31 05 | Project Superintendent | 165000
01 31 00 | 01 31 06 | Project Foreman | 0
01 32 00 | 01 32 00 | Travel
01 41 00 |  | Permits | 3000
01 45 00 |  | Quality Control | 8000
01 51 00 |  | Temporary Utilities | 15000
01 52 00 |  | Construction Facilities | 35468.0789
01 52 00 | 01 52 01 | Construction Field Office | 12375
01 52 00 | 01 52 02 | Sanitary Facilities | 12000
01 52 00 | 01 52 03 | Drawing Reprographics | 5503.0789
01 52 00 | 01 52 04 | First-Aid / Safety | 3750
01 52 00 | 01 52 05 | Job Sign | 0
01 54 00 |  | Construction Aids | 203313.0434
01 55 00 | 01 55 00 | Winter Conditions
01 56 00 |  | Temporary Barriers & Enclosures | 25000
01 74 00 |  | Cleaning & Waste Management | 54500
01 74 00 | 01 74 01 | Progress Cleaning | 0
01 74 00 | 01 74 02 | Site Maintenance | 14400
01 74 00 | 01 74 03 | Construction Waste Mgmt & Disposal | 16500
01 74 00 | 01 74 04 | Final Cleaning | 23600
02 00 00 |  | Existing Conditions | 0
02 41 00 |  | Demolition | 0
02 82 00 |  | Asbestos Remediation | 0
02 83 00 |  | Trenching | 0
03 00 00 |  | Concrete | 670607.8609
03 11 00 |  | Concrete Forming | 302400
03 20 00 |  | Concrete Reinforcing | 0
03 30 00 |  | Cast-in-Place Concrete | 177795.8609
03 35 00 |  | Concrete Finishing | 44527
03 40 00 |  | Precast Concrete | 77850
03 60 00 |  | Foundation Materials | 68035
03 60 00 | 03 60 01 | Insulation | 15640
03 60 00 | 03 60 02 | Vapour Barrier | 8235
04 00 00 |  | Masonry | 140360
04 20 00 |  | Unit Masonry | 140360
04 43 00 |  | Stone Masonry | 0
05 00 00 |  | Metals | 214970
05 12 00 |  | Structural Steel Framing | 141400
05 20 00 |  | Metal Joists | 0
05 30 00 |  | Metal Decking | 0
05 51 00 |  | Metal Stairs | 0
05 52 00 |  | Metal Railings | 73570
05 59 00 |  | Metal Specialties | 0
06 00 00 |  | Wood, Plastics, and Composites | 2574857.5544
06 11 00 |  | Framing Labour | 571330
06 20 00 |  | Framing Material | 1261823.66
06 22 00 |  | Millwork | 425900
06 41 00 |  | Architechtural Wood Casework | 0
06 42 00 |  | Wood Paneling | 0
06 43 00 |  | Wood Stairs and Railings | 0
06 46 00 |  | Wood Trim | 315803.8944
06 48 00 |  | Wood Frames | 0
07 00 00 |  | Thermal and Moisture Protection | 1179521.014
07 21 00 |  | Thermal Insulation | 237835
07 24 00 |  | EIFS | 271678.014
07 31 00 |  | Shingles | 81750
07 42 00 |  | Wall Panels | 0
07 46 00 |  | Siding | 561708
07 52 00 |  | Modified Bituminous Membrane Roofing | 0
07 53 00 |  | Elastomeric Membrane Roofing | 0
07 62 00 |  | Sheet Metal Flashing and Trim | 0
07 63 00 |  | Sheet Metal Roofing Specialties | 0
07 64 00 |  | Sheet Metal Wall Cladding | 0
07 72 00 |  | Roof Accessories | 0
07 81 00 |  | Applied Fireproofing | 26550
07 90 00 |  | Joint Protection | 0
08 00 00 |  | Openings | 274429.81
08 11 00 |  | Metal Doors and Frames | 89875
08 14 00 |  | Wood Doors | 0
08 31 00 |  | Access Doors and Panels | 8000
08 32 00 |  | Sliding Gates | 0
08 33 00 |  | Coiling Doors and Drilles | 10984.51
08 34 00 |  | Special Function Doors | 0
08 38 00 |  | Traffic Doors | 0
08 41 00 |  | Entrances and Storefronts | 39425
08 44 00 |  | Curtain Wall and Glazed Assemblies | 0
08 50 00 |  | Windows | 126145.3
08 70 00 |  | Hardware | 0
08 81 00 |  | Glass Glazing | 0
08 83 00 |  | Mirrors | 0
08 87 00 |  | Glazing Surface Films | 0
08 91 00 |  | Louvers | 0
09 00 00 |  | Finishes | 1747325
09 20 00 |  | Plaster and Gypsum Board | 1139222
09 30 00 |  | Tiling | 0
09 50 00 |  | Ceiling | 0
09 60 00 |  | Flooring | 411100
09 60 00 | 09 61 00 | Concrete Floor Polishing | 121100
09 60 00 | 09 62 00 | Specialty Flooring | 0
09 60 00 | 09 64 00 | Wood Flooring | 0
09 60 00 | 09 65 00 | VCT | 0
09 60 00 | 09 67 00 | LVT | 290000
09 60 00 | 09 68 00 | Carpet Tile | 0
09 72 00 |  | Wall Coverings | 0
09 91 00 |  | Painting | 197003
10 00 00 |  | Specialties | 88173.76
10 11 00 |  | Visual Display Units | 0
10 14 00 |  | Signage | 10950
10 20 00 |  | Interior Specialties | 11989.39
10 44 00 |  | Fire Protection Specialties | 0
10 51 00 |  | Lockers | 31062.37
10 57 00 |  | Wardrobe and Closet Specialties | 32532
10 70 00 |  | Exterior Specialties | 1640
11 00 00 |  | Equipment | 200600
11 11 00 |  | Vehicle Service Equipment | 0
11 13 00 |  | Loading Dock Equipment | 0
11 30 00 |  | Residential Equipment | 200600
11 41 00 |  | Food Storage Equipment | 0
11 48 00 |  | Food service Cleaning and Disposal Equipment | 0
11 52 00 |  | Audio-Visual Equipment | 0
11 53 00 |  | Laboratory Equipment | 0
12 00 00 |  | Furnishings | 41300
12 20 00 |  | Window Treatments | 0
12 21 00 |  | Window Blinds | 41300
12 30 00 |  | Casework | 0
12 32 00 |  | Manufactured Wood Casework | 0
12 35 00 |  | Specialty Casework | 0
12 36 00 |  | Countertops | 0
13 00 00 |  | Special Construction | 121400
14 00 00 |  | Conveying Equipment | 155285
14 20 00 |  | Elevators | 0
14 40 00 |  | Lifts | 0
14 42 00 |  | Wheelchair Lifts | 0
21 00 00 |  | Fire Suppression | 212000
21 10 00 |  | Water-Based Fire-Suppression System | 212000
22 00 00 |  | Plumbing | 674850
22 10 00 |  | Plumbing Piping | 674850
22 30 00 |  | Plumbing Equipment | 0
22 40 00 |  | Plumbing Fixtures | 0
22 42 00 |  | Commercial Plumbing Fixtures | 0
22 45 00 |  | Emergency Plumbing Fixtures | 0
22 47 00 |  | Drinking Fountains and Water Coolers | 0
23 00 00 |  | Heating, Ventilating, and Air Conditioning | 467650
23 07 00 |  | HVAC Insulation | 467650
23 08 00 |  | Commissioning of HVAC | 0
23 09 00 |  | Instrumentation and Control for HVAC | 0
23 10 00 |  | Facility Fuel System | 0
23 13 00 |  | Facility Fuel Storage | 0
23 20 00 |  | HVAC Piping and Pumps | 0
23 23 00 |  | Refrigerant Piping | 0
23 30 00 |  | HVAC Air Distribution | 0
23 70 00 |  | Central HVAC Equipment | 0
23 83 00 |  | Radiant Heating Units | 0
25 00 00 |  | Integrated Automation | 0
26 00 00 |  | Electrical | 822897
26 09 00 |  | Instrumentation and Controls for Electrical Systems | 770000
26 10 00 |  | Medium-Voltage Electrical Distribution | 0
26 50 00 |  | Lighting | 52897
27 00 00 |  | Communications | 0
27 10 00 |  | Structured Cabling | 0
27 20 00 |  | Data Communications | 0
27 30 00 |  | Voice Communications | 0
27 40 00 |  | Audio-Voice Communications | 0
27 50 00 |  | Distributed Communications and Monitoring Systems | 0
28 00 00 |  | Electronic Safety and Security | 0
28 10 00 |  | Access Control | 0
28 20 00 |  | Video Surveillance | 0
28 30 00 |  | Security Detection, Aarm, and Monitoring | 0
28 40 00 |  | Life Safety | 0
31 00 00 |  | Earthwork | 268300
31 10 00 |  | Site Clearing | 0
31 20 00 |  | Earth Moving | 268300
31 37 00 |  | Riprap | 0
31 70 00 |  | Tunneling | 0
32 00 00 |  | Exterior Improvements | 151071.01
32 10 00 |  | Bases, Ballasts, and Paving | 53250
32 16 00 |  | Curbs, Gutters, Sidewalks, and Driveways | 28809.84
32 17 00 |  | Paving Specialties | 960
32 30 00 |  | Site Improvements | 16800
32 90 00 |  | Planting | 51251.17
33 00 00 |  | Utilities | 0
33 10 00 |  | Water Utilities | 0
33 30 00 |  | Sanitary Sewerage | 0
33 70 00 |  | Electrical Utilities | 0

## DATA
| Quarter | Column1 | Province |  |  |  | Project Definition |  | Contract Type | Payment Method |  | A | >5M
| Q1 |  | NB |  |  |  | Multi Residential |  | CCDC 2 | Stipulated Price |  | B | 2-5M
| Q2 |  | PEI |  |  |  | Office |  | CCDC 5B | Fixed Fee |  | C | 500K - 2M |  |  |  | Status |  | Result
| Q3 |  | NS |  |  |  | Retail |  | CCDC 5A |  |  | D | 100K - 500K |  |  |  | Awarded |  | Successful
| Q4 |  | Other |  |  |  | Food |  | Design Build |  |  | E | less than 100K |  |  |  | Not Awarded |  | Unsuccessful
Pending
Closing Date | Budget Year | Quarter | Province | City/Town | Estimate Number | Estimate Name | Type of Construction | Area | Contract Type | Payment Method | Estimate Price | Price Category | Schedule | Soft Cost | Cost per Week | Margin | Status | Bid Docs | Successful / Unsuccessful
2024-03-28 | 2024 | Q2 | NB | Moncton | 2989 | 2500 Mountain Road Multi-Res | 0 | 65592 | CCDC 5B | Fixed Fee | 11119373.0882 | A | 60 | 737710.0788 | 12295.168 | 6.634% | 0 | 0 | 0

## Estimate Version Comparison
2500 Mountain Road Multi-Res | [5 empty] | CLIENT SUMMARY
Ashish Goel
Date: | 2024-03-28
|  |  |  | 45379 | 0
01 00 00 | General Requirements |  | 0 |  | 509281.1223 |  | Increase | 509281.1223
01 11 00 | Preconstruction Costs | 0 |  | 0
01 31 00 | Project Management and Coordination | 0 |  | 165000
01 41 00 | Permits | 0 |  | 3000
01 45 00 | Quality Control | 0 |  | 8000
01 51 00 | Temporary Utilities | 0 |  | 15000
01 52 00 | Construction Facilities | 0 |  | 35468.0789
01 54 00 | Construction Aids | 0 |  | 203313.0434
01 56 00 | Temporary Barriers & Enclosures | 0 |  | 25000
01 74 00 | Cleaning & Waste Management | 0 |  | 54500
02 00 00 | Existing Conditions |  | 0 |  | 0 |  | Decrease or No Change | 0
02 41 00 | Demolition | 0 |  | 0
02 82 00 | Asbestos Remediation | 0 |  | 0
02 83 00 | Trenching | 0 |  | 0
03 00 00 | Concrete |  | 0 |  | 670607.8609 |  | Increase | 670607.8609
03 11 00 | Concrete Forming | 0 |  | 302400
03 20 00 | Concrete Reinforcing | 0 |  | 0
03 30 00 | Cast-in-Place Concrete | 0 |  | 222322.8609
03 40 00 | Precast Concrete | 0 |  | 77850
03 60 00 | Grouting | 0 |  | 68035
04 00 00 | Masonry |  | 0 |  | 140360 |  | Increase | 140360
04 20 00 | Unit Masonry | 0 |  | 140360
04 40 00 | Stone Assemblies | 0 |  | 0
05 00 00 | Metals |  | 0 |  | 214970 |  | Increase | 214970
05 12 00 | Structural Steel Framing | 0 |  | 141400
05 20 00 | Metal Joists | 0 |  | 0
05 30 00 | Metal Decking | 0 |  | 0
05 50 00 | Metal Fabrications | 0 |  | 73570
06 00 00 | Wood, Plastics, and Composites |  | 0 |  | 2574857.5544 |  | Increase | 2574857.5544
06 11 00 | Framing Labour | 0 |  | 571330
06 11 00 | Framing Material | 0 |  | 1261823.66
06 22 00 | Millwork | 0 |  | 425900
06 40 00 | Architectural Woodwork | 0 |  | 315803.8944
07 00 00 | Thermal and Moisture Protection |  | 0 |  | 1179521.014 |  | Increase | 1179521.014
07 21 00 | Thermal Insulation | 0 |  | 237835
07 24 00 | EIFS | 0 |  | 271678.014
07 31 00 | Shingles | 0 |  | 81750
07 42 00 | Wall Panels | 0 |  | 0
07 46 00 | Siding | 0 |  | 561708
07 50 00 | Membrane Roofing | 0 |  | 0
07 60 00 | Flashing and Sheet Metal | 0 |  | 0
07 72 00 | Roof Accessories | 0 |  | 0
07 80 00 | Smoke and Fire Protection | 0 |  | 26550
07 90 00 | Joint Protection | 0 |  | 0
08 00 00 | Openings |  | 0 |  | 274429.81 |  | Increase | 274429.81
08 10 00 | Doors and Frames | 0 |  | 89875
08 30 00 | Speciality Doors and Frames | 0 |  | 18984.51
08 40 00 | Store Fronts and Curtainwalls | 0 |  | 39425
08 50 00 | Windows | 0 |  | 126145.3
08 70 00 | Hardeware | 0 |  | 0
08 80 00 | Glazing | 0 |  | 0
08 90 00 | Louvers | 0 |  | 0
09 00 00 | Finishes |  | 0 |  | 1747325 |  | Increase | 1747325
09 20 00 | Plaster and Gypsum Board | 0 |  | 1139222
09 30 00 | Tiling | 0 |  | 0
09 50 00 | Ceiling | 0 |  | 0
09 60 00 | Flooring | 0 |  | 411100
09 70 00 | Wall Finishes | 0 |  | 0
09 90 00 | Painting | 0 |  | 197003
10 00 00 | Specialties |  | 0 |  | 55641.76 |  | Increase | 55641.76
10 11 00 | Visual Display Units | 0 |  | 0
10 14 00 | Signage | 0 |  | 10950
10 20 00 | Interior Specialties | 0 |  | 11989.39
10 40 00 | Safety Specialties | 0 |  | 0
10 50 00 | Storage Specialties | 0 |  | 31062.37
10 70 00 | Exterior Specialties | 0 |  | 1640
11 00 00 | Equipment |  | 0 |  | 200600
11 10 00 | Vehicle Equipment | 0 |  | 0
11 30 00 | Residential Equipment | 0 |  | 200600 |  |  | Decrease or No Change | 0
11 40 00 | Food Service Equipment | 0 |  | 0
11 50 00 | Educational & Lab Equipment | 0 |  | 0
12 00 00 | Furnishings |  | 0 |  | 41300 |  | Increase | 41300
12 20 00 | Window Treatments | 0 |  | 41300
12 30 00 | Casework | 0 |  | 0
13 00 00 | Special Construction |  | 0 |  | 121400 |  | Increase | 121400
14 00 00 | Conveying Equipment |  | 0 |  | 0 |  | Decrease or No Change | 0
14 20 00 | Elevators | 0 |  | 0
14 40 00 | Lifts | 0 |  | 0
21 00 00 | Fire Suppression |  | 0 |  | 212000 |  | Decrease or No Change | 0
21 10 00 | Water-Based Fire-Suppression System | 0 |  | 212000
22 00 00 | Plumbing |  | 0 |  | 674850 |  | Decrease or No Change | 0
22 10 00 | Plumbing Piping | 0 |  | 674850
22 30 00 | Plumbing Equipment | 0 |  | 0
22 40 00 | Plumbing Fixtures | 0 |  | 0
23 00 00 | HVAC |  | 0 |  | 467650 |  | Decrease or No Change | 0
23 07 00 | HVAC Insulation | 0 |  | 467650
23 08 00 | Commissioning of HVAC | 0 |  | 0
23 09 00 | Instrumentation and Control for HVAC | 0 |  | 0
23 10 00 | Facility Fuel System | 0 |  | 0
23 20 00 | HVAC Piping and Pumps | 0 |  | 0
23 30 00 | HVAC Air Distribution | 0 |  | 0
23 70 00 | Central HVAC Equipment | 0 |  | 0
23 80 00 | Decentralized HVAC Equipment | 0 |  | 0
25 00 00 | Integrated Automation |  | 0 |  | 0 |  | Decrease or No Change | 0
26 00 00 | Electrical |  | 0 |  | 822897 |  | Decrease or No Change | 0
26 09 00 | Sub Contractor Cost | 0 |  | 770000
26 10 00 | Electrical Distribution | 0 |  | 0
26 50 00 | Lighting | 0 |  | 52897
27 00 00 | Communications |  | 0 |  | 0 |  | Decrease or No Change | 0
27 10 00 | Structured Cabling | 0 |  | 0
27 20 00 | Data Communications | 0 |  | 0
27 30 00 | Voice Communications | 0 |  | 0
27 40 00 | Audio-Voice Communications | 0 |  | 0
27 50 00 | Distributed Communications and Monitoring Systems | 0 |  | 0
28 00 00 | Electronic Safety and Security |  | 0 |  | 0 |  | Decrease or No Change | 0
28 10 00 | Access Control | 0 |  | 0
28 20 00 | Video Surveillance | 0 |  | 0
28 30 00 | Security Detection, Aarm, and Monitoring | 0 |  | 0
28 40 00 | Life Safety | 0 |  | 0
31 00 00 | Earthwork |  | 0 |  | 268300 |  | Increase | 268300
31 10 00 | Site Clearing | 0 |  | 0
31 20 00 | Earth Moving | 0 |  | 268300
31 30 00 | Earthwork Methods | 0 |  | 0
31 70 00 | Tunneling | 0 |  | 0
32 00 00 | Exterior Improvements |  | 0 |  | 151071.01 |  | Increase | 151071.01
32 10 00 | Bases, Ballasts, and Paving | 0 |  | 83019.84
32 30 00 | Site Improvements | 0 |  | 16800
32 90 00 | Planting | 0 |  | 51251.17
33 00 00 | Utilities |  | 0 |  | 0 |  | Decrease or No Change | 0
33 10 00 | Water Utilities | 0 |  | 0
33 30 00 | Sanitary Sewerage | 0 |  | 0
33 40 00 | Stormwater Utilities | 0 |  | 0
33 70 00 | Electrical Utilities | 0 |  | 0
| Fee |  |  | 529493.9566 |  |  | Increase | 529493.9566
| Total (HST Excluded) | 0 |  | 10856556.0882 |  |  | Increase | 10856556.0882

## Client Detailed Summary
2500 Mountain Road Multi-Res |  | CLIENT SUMMARY
Date: | 2024-05-09
01 00 00 | General Requirements |  |  | 584281.1223
01 11 00 | Preconstruction Costs |  | 0
01 31 00 | Project Management and Coordination |  | 165000
01 32 00 | Insurance |  | 0 | By Client
01 41 00 | Permits |  | 3000 | By Client
01 45 00 | Quality Control |  | 8000
01 51 00 | Temporary Utilities |  | 15000
01 52 00 | Construction Facilities |  | 35468.0789
01 54 00 | Security |  | 30000
01 54 00 | Construction Aids & Winter Conditions |  | 248313.0434
01 56 00 | Temporary Barriers & Enclosures |  | 25000
01 74 00 | Cleaning & Waste Management |  | 54500
02 00 00 | Existing Conditions |  |  | 0
02 41 00 | Demolition |  | 0
02 82 00 | Asbestos Remediation |  | 0
02 83 00 | Trenching |  | 0
03 00 00 | Concrete |  |  | 670607.8609
03 11 00 | Concrete Forming |  | 302400
03 20 00 | Concrete Reinforcing |  | 0
03 30 00 | Cast-in-Place Concrete |  | 222322.8609
03 40 00 | Precast Concrete |  | 77850
03 60 00 | Grouting |  | 68035
04 00 00 | Masonry |  |  | 140360
04 20 00 | Exterior Stone Veneer |  | 140360
04 40 00 | Stone Assemblies |  | 0
05 00 00 | Metals |  |  | 214970
05 12 00 | Structural Steel Framing |  | 141400
05 20 00 | Metal Joists |  | 0
05 30 00 | Metal Decking |  | 0
05 50 00 | Balcony Handrails |  | 73570
06 00 00 | Wood, Plastics, and Composites |  |  | 2574857.5544
06 11 00 | Framing Labour |  | 571330
06 11 00 | Framing Material |  | 1261823.66
06 22 00 | Millwork |  | 425900
06 40 00 | Architectural Woodwork |  | 315803.8944
07 00 00 | Thermal and Moisture Protection |  |  | 1179521.014
07 21 00 | Thermal Insulation |  | 237835
07 24 00 | Acoustiboard floor soundproofing |  | 271678.014
07 31 00 | Shingles |  | 81750
07 42 00 | Wall Panels |  | 0
07 46 00 | Siding |  | 561708
07 50 00 | Membrane Roofing |  | 0
07 60 00 | Flashing and Sheet Metal |  | 0
07 72 00 | Roof Accessories |  | 0
07 80 00 | Smoke and Fire Protection |  | 26550
07 90 00 | Joint Protection |  | 0
08 00 00 | Openings |  |  | 274429.81
08 10 00 | Doors and Frames |  | 89875
08 30 00 | Speciality Doors and Frames |  | 18984.51
08 40 00 | Aluminum Doors and Glazing |  | 39425
08 50 00 | Windows |  | 126145.3
08 70 00 | Hardeware |  | 0
08 80 00 | Glazing |  | 0
08 90 00 | Louvers |  | 0
09 00 00 | Finishes |  |  | 1747325
09 20 00 | Plaster and Gypsum Board |  | 1139222
09 30 00 | Tiling |  | 0
09 50 00 | Ceiling |  | 0
09 60 00 | Flooring |  | 411100
09 70 00 | Wall Finishes |  | 0
09 90 00 | Painting |  | 197003
10 00 00 | Specialties |  |  | 88173.76
10 11 00 | Visual Display Units |  | 0
10 14 00 | Mailbox |  | 10950
10 20 00 | Washroom Specialties |  | 11989.39
10 40 00 | Closet shelving |  | 32532
10 50 00 | Storage Specialties |  | 31062.37
10 70 00 | Bike Rack |  | 1640
11 00 00 | Equipment |  |  | 200600
11 10 00 | Vehicle Equipment |  | 0
11 30 00 | Appliances |  | 200600
11 40 00 | Food Service Equipment |  | 0
11 50 00 | Educational & Lab Equipment |  | 0
12 00 00 | Furnishings |  |  | 41300
12 20 00 | Window Treatments |  | 41300
12 30 00 | Casework |  | 0
13 00 00 | Solar Panel Addition |  |  | 121400
| Solar Panel System |  | 96400
| Framing |  | 25000
| Electrical |  | 0
14 00 00 | Conveying Equipment |  |  | 155285
14 20 00 | Elevators |  | 155285
14 40 00 | Lifts |  | 0
21 00 00 | Fire Suppression |  |  | 212000
21 10 00 | Water-Based Fire-Suppression System |  | 212000
22 00 00 | Plumbing |  |  | 674850
22 10 00 | Plumbing |  | 674850
22 30 00 | Plumbing Equipment |  | 0
22 40 00 | Plumbing Fixtures |  | 0
23 00 00 | HVAC |  |  | 467650
23 07 00 | HVAC |  | 467650
23 08 00 | Commissioning of HVAC |  | 0
23 09 00 | Instrumentation and Control for HVAC |  | 0
23 10 00 | Facility Fuel System |  | 0
23 20 00 | HVAC Piping and Pumps |  | 0
23 30 00 | HVAC Air Distribution |  | 0
23 70 00 | Central HVAC Equipment |  | 0
23 80 00 | Decentralized HVAC Equipment |  | 0
25 00 00 | Integrated Automation |  |  | 0
26 00 00 | Electrical |  |  | 822897
26 09 00 | Electrical |  | 770000
26 10 00 | Solar Panels |  | 0
26 50 00 | Lighting |  | 52897
27 00 00 | Communications |  |  | 0
27 10 00 | Structured Cabling |  | 0
27 20 00 | Data Communications |  | 0
27 30 00 | Voice Communications |  | 0
27 40 00 | Audio-Voice Communications |  | 0
27 50 00 | Distributed Communications and Monitoring Systems |  | 0
28 00 00 | Electronic Safety and Security |  |  | 0
28 10 00 | Access Control |  | 0
28 20 00 | Video Surveillance |  | 0
28 30 00 | Security Detection, Aarm, and Monitoring |  | 0
28 40 00 | Life Safety |  | 0
31 00 00 | Earthwork |  |  | 268300
31 10 00 | Site Clearing |  | 0
31 20 00 | Earth Moving |  | 268300
31 30 00 | Earthwork Methods |  | 0
31 70 00 | Tunneling |  | 0
32 00 00 | Exterior Improvements |  |  | 151071.01
32 10 00 | Bases, Ballasts, and Paving |  | 54210
32 16 00 | Curb & Sidewalks |  | 28809.84
32 30 00 | Bollards |  | 16800
32 90 00 | Planting |  | 51251.17
33 00 00 | Utilities |  |  | 0
33 10 00 | Water Utilities |  | 0
33 30 00 | Sanitary Sewerage |  | 0
33 40 00 | Stormwater Utilities |  | 0
33 70 00 | Electrical Utilities |  | 0
| Subtotal |  | 10589879.1316
| Fee |  | 529493.9566
| Subtotal |  | 11119373.0882
| Recommended Contingency |  | By Client
| Already Spent |  | 1243730.75
| Total (HST Excluded) |  | 12363103.8382 |  | 0
209544.1329
188.4849

## Estimate Summary
Project Information
Closing Date : | 2024-03-28
Estimate # E- | 2989 | Area: | 65592
Province : | NB | Estimate Name : | 2500 Mountain Road Multi-Res | Bid Documents :
City/Town : | Moncton | Client : | Ashish Goel | Status :
Budget Year : | 2024 | Contract Type : | CCDC 5B | Result:
Quarter: | Q2 | Payment Method : | Fixed Fee
|  | Area: | 65592 | Sq. Ft. |  |  |  |  | Belle Foret | 77648 | SF
CODE | DESCRIPTION |  | M&E $$ | M-HRS | LAB $$ | SUB CONT. | Total |  | Comparable Project
|  | % | [5 empty] | $/SF
01 00 00 | General Requirements | 5.517% | 401881.1223 | 241 | 179400 | 3000 | 584281.1223 | 9$/SF | 856794.47 | 11.0343
02 00 00 | Existing Conditions | 0% | 0 | 0 | 0 | 0 | 0 | 0$/SF
03 00 00 | Concrete | 6.333% | 236330.8609 | 158.3333 | 9500 | 424777 | 670607.8609 | 10.3$/SF | 1469855.97 | 18.9297
04 00 00 | Masonry | 1.325% | 0 | 0 | 0 | 140360 | 140360 | 2.2$/SF | 240000 | 3.0909
05 00 00 | Metals | 2.03% | 800 | 0 | 0 | 214170 | 214970 | 3.3$/SF | 141945.5 | 1.8281
06 00 00 | Wood, Plastics, and Composites | 24.31% | 551103.8944 | 0 | 0 | 2023753.66 | 2574857.5544 | 39.3$/SF | 2971859.63 | 38.2735
07 00 00 | Thermal and Moisture Protection | 11.14% | 545786.814 | 59077.8 | 99349.2 | 534385 | 1179521.014 | 18$/SF | 1267203.65 | 16.3198
08 00 00 | Openings | 2.591% | 8000 | 0 | 0 | 266429.81 | 274429.81 | 4.2$/SF | 508342.1 | 6.5468
09 00 00 | Finishes | 16.5% | 121100 | 0 | 0 | 1626225 | 1747325 | 26.7$/SF | 1804882.75 | 23.2444
10 00 00 | Specialties | 0.8326% | 13329.39 | 5 | 300 | 74544.37 | 88173.76 | 1.4$/SF | 101680 | 1.3095
11 00 00 | Equipment | 1.894% | 200600 | 0 | 0 | 0 | 200600 | 3.1$/SF | 234000 | 3.0136
12 00 00 | Furnishings | 0.39% | 41300 | 0 | 0 | 0 | 41300 | 0.7$/SF | 47669 | 0.61391
13 00 00 | Special Construction | 1.146% | 10000 | 0 | 0 | 111400 | 121400 | 1.9$/SF
14 00 00 | Conveying Equipment | 1.466% | 0 | 0 | 0 | 155285 | 155285 | 2.4$/SF | 324859 | 4.1837
21 00 00 | Fire Suppression | 2.002% | 0 | 0 | 0 | 212000 | 212000 | 3.3$/SF | 256043.6 | 3.2975
22 00 00 | Plumbing | 6.373% | 0 | 0 | 0 | 674850 | 674850 | 10.3$/SF | 813490.08 | 10.4766
23 00 00 | HVAC | 4.416% | 0 | 0 | 0 | 467650 | 467650 | 7.2$/SF | 641638.63 | 8.2634
25 00 00 | Integrated Automation | 0% | 0 | 0 | 0 | 0 | 0 | 0$/SF
26 00 00 | Electrical | 7.771% | 52897 | 0 | 0 | 770000 | 822897 | 12.6$/SF | 1110432.08 | 14.3008
27 00 00 | Communications | 0% | 0 | 0 | 0 | 0 | 0 | 0$/SF
28 00 00 | Electronic Safety and Security | 0% | 0 | 0 | 0 | 0 | 0 | 0$/SF
31 00 00 | Earthwork | 2.534% | 40000 | 0 | 0 | 228300 | 268300 | 4.1$/SF | 771509.48 | 9.936
32 00 00 | Exterior Improvements | 1.427% | 0 | 0 | 0 | 151071.01 | 151071.01 | 2.4$/SF | 211970 | 2.7299
33 00 00 | Utilities | 0% | 0 | 0 | 0 | 0 | 0 | 0$/SF
| Sub Totals>>>>>> | 100% | 2223129.0816 | 59482.1333 | 288549.2 | 8078200.85 | 10589879.1316 | 161.5$/SF
| Total Construction Cost>>>>>> |  | 10589879.1316
[12 empty] | Total Job | 12246312.69
| OH&P>>>>>> |  | 529493.9566 | 5% |  |  |  |  | 8974.4738 |  |  | Ready to award / Awarded | 8049129.88
[5 empty] | HST | TOTAL | [5 empty] | % | 0.65727
15%
| Estimated Price |  | 11119373.0882 |  | 1667905.9632 | 12787279.0514
Budget
[5 empty] | HST | TOTAL |  |  | 11301598.07
| Total (HST excluded) |  | 11119373.0882 |  | 1667905.9632 | 12787279.0514 |  |  | Difference
182224.9818
|  |  | 169.5233 | /sq.ft. | 188463.9506
|  | Schedule | 60 | Weeks |  | Job Type | Target Margin
|  | Soft Cost | 737710.0788 | 12295.168 |  | A > 1,000,000 | 10%
[6 empty] | B > 500,000 | 15%
|  | Margin | 6.634% |  |  | C > 100,000 | 20%
|  | Buyouts | 111193.7309 | 1% |  | D < 100,000 | 25%
|  | CO's | 555968.6544 | 5%
Competititors on Bid | 0
277984.3272
11397357.4154

## 1
0
[6 empty] | General Requirements |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
01 11 00 | Preconstruction Costs | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 11 13 | Senior Construction Manager |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 16 | Senior Estimator |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 19 | Junior Estimator |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 23 | Reprographics |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26 | Design Costs |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.13 | Architectural |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.16 | Civil |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.19 | Structural |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.23 | HVAC |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.26 | Plumbing |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.29 | Electrical |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 11 26.33 | Geotechnical |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 31 00 | Project Management and Coordination | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 31 01 | Senior Construction Manager |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 31 02 | Senior Estimator |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 31 03 | Senior Project Manager | 60 | LS | 0 | 0 |  | 100 | 0 |  | 0
01 31 04 | Project Coordinator | 60 | LS | 0 | 0 |  | 75 | 0 |  | 0
01 31 05 | Project Superintendent | 60 | LS | 0 | 0 | 1 | 2750 | 165000 |  | 165000 | Ekinox | 188344 | Spent to date $168k
01 31 06 | Project Foreman |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
0
[9 empty] | Sub Total | 165000
CODE | DESCRIPTION
01 32 00 | Insurance |  | /$1000 | Cost | Rate | Toll Cost | Frequency |  | Sub Total | Total
01 32 01 | General Liability & Contractor's Pollution Liability | 10005.598 | /$1000 | 0.63 | [5 empty] | 0
| Contractor's Pollution Liability | 10005.598 | /$1000 | 1.29 | [5 empty] | 0 | By Client
| Builders Risk | 13.3333 | $1000/month | 0.75 | [5 empty] | 0 | Ekinox | 188344
| Wrap-up Liability | 10005.598 | /$1000 | 1.88 | [5 empty] | 0
01 32 00 | [8 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
CODE | DESCRIPTION
01 32 00 | Travel | Frequency | Weeks | Distance (Round Trip) | Rate | Toll Cost | Frequency |  | Sub Total | Total
| PM KM |  | 60 | 0 | 0.45 |  | 0 |  | 0 | 0
| Superintendent KM |  | 60 | 0 | 0.45 |  | 0 |  | 0 | 0
| Hotel |  | 60 |  | 120 |  |  |  | 0 | 0
Per Diem
| foreman - Mondays |  | 60 |  | 40 |  |  |  | 0 | 0
| foreman: Tues to Thurs |  | 60 |  | 47 |  |  |  | 0 | 0
| foreman: Fridays |  | 60 |  | 22 |  |  |  | 0 | 0
01 32 00 | [8 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 41 00 | Permits | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 41 00 | Bldg Permit Fees | 10005.598 | /$1000 | 0 | 0 |  |  |  | 3000 | 3000 | By Client
| Moncton | 8 | /$1000 | "+ Development Fee |  | $100 <$500k, $150 $500k to 1M, $300 1M - 5 M, $500 > 5M
| Dieppe | 7.5 | /$1000
| Saint John | 8.9 | /$1000 | $120 Base Fee
| Fredericton | 8 | /$1000
| Halifax | 5.5 | /$1000
[9 empty] | Sub Total | 3000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 45 00 | Quality Control | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 45 01 | Soil Investigation and Testing | 1 | LS | 2500 | 2500 |  | 0 | 0 |  | 2500
01 45 02 | Material Inspection and Testing | 1 | LS | 2500 | 2500 |  | 0 | 0 |  | 2500 | Ekinox | 25768
01 45 03 | Survey and Layout | 1 | LS | 3000 | 3000 |  | 0 | 0 |  | 3000
01 45 04 | Hazardous Idendification Inspection |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 45 05 | Sanitary Line Video |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 8000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 51 00 | Temporary Utilities | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 51 01 | Temporary Fire Protection |  | Week | 0 | 0 |  | 0 | 0 |  | 0
01 51 02 | Temporary Power | 60 | Week | 250 | 15000 |  | 0 | 0 |  | 15000 | Ekinox | 16732.93
01 51 03 | Temporary Lighting |  | Week | 0 | 0 |  | 0 | 0 |  | 0
01 51 04 | Temporary Fuel Oil |  | Week | 0 | 0 |  | 0 | 0 |  | 0
01 51 05 | Temp HVAC |  | Week | 0 | 0 |  | 0 | 0 |  | 0
01 51 06 | Temporary Internet |  | Week | 0 | 0 |  | 0 | 0 |  | 0
01 51 07 | Temporary Water |  | Week | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 15000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 52 00 | Construction Facilities | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 52 01 | Construction Field Office | 15 | Month | 825 | 12375 |  | 0 | 0 |  | 12375
01 52 01 | Field Office One Time Charges | 1 | Ea | 1840 | 1840 |  |  |  |  | 1840
01 52 02 | Sanitary Facilities | 240 | Week | 50 | 12000 |  | 0 | 0 |  | 12000 | Ekinox | 32020
01 52 03 | Drawing Reprographics | 10005.598 | M | 0.55 | 5503.0789 |  | 0 | 0 |  | 5503.0789
01 52 04 | First-Aid / Safety | 30 | Week | 125 | 3750 |  | 0 | 0 |  | 3750
01 52 05 | Job Sign |  | Ea | 200 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 35468.0789
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 54 00 | Construction Aids | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 54 01 | Security | 1 | LS | 30000 | 30000 |  | 0 | 0 |  | 30000 | Ekinox | 30000
01 54 02 | Rentals | 15 | LS | 10000 | 150000 |  | 0 | 0 |  | 150000
01 54 03 | Small Tools | 0 | Allow | 0 | 0 |  | 0 | 0 |  | 0 | Ekinox | 127609
01 54 04 | Technology (Procore, Smartbid, On-screen, Imaginit, Sage 300) | 10005.598 | /$1000 | 2.33 | 23313.0434 |  | 0 | 0 |  | 23313.0434
[9 empty] | Sub Total | 203313.0434
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 55 00 | Winter Conditions | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 55 01 | Winter Conditions | 5 | month | 15000 | 75000 |  |  |  |  | 75000 | Ekinox | 72459.76
01 55 02 | Tarps (10) |  | ea | 73 | 0 |  |  |  |  | 0
01 55 03 | Fans |  | month | 355 | 0 |  |  |  |  | 0
01 55 04 | Fuel Cube |  | month | 609 | 0 |  |  |  |  | 0
01 55 05 | Delivery |  | ea | 98 | 0 |  |  |  |  | 0
01 55 06 | Pickup |  | ea | 98 | 0 |  |  |  |  | 0
Quantity of Fuel
|  | Tank Size | L/Hr | Running (Hours / Day) | Litres / Day | Duration (Days)
|  | 90 | 6 | 24 | 144 | 0
01 55 07 | Fuel | 0 | L | 1.3 | 0 |  |  |  |  | 0
[9 empty] | Sub Total | 75000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 56 00 | Temporary Barriers & Enclosures | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 56 01 | Air/Dust Barriers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 56 02 | Temp Barricades |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Ekinox | 21600
01 56 03 | Temporary Fencing | 1 | LS | 25000 | 25000 |  | 0 | 0 |  | 25000
01 56 04 | Hoarding |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 25000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
01 74 00 | Cleaning & Waste Management | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
01 74 01 | Progress Cleaning |  | LS | 0 | 0 |  | 0 | 0 |  | 0
01 74 02 | Site Maintenance |  | LS | 0 | 0 | 240 | 60 | 14400 |  | 14400
01 74 03 | Construction Waste Mgmt & Disposal | 30 | ea | 550 | 16500 |  | 0 | 0 |  | 16500
01 74 04 | Final Cleaning | 59 | Unit | 400 | 23600 |  | 0 | 0 |  | 23600
[9 empty] | Sub Total | 54500
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 1
8.9078 |  |  |  |  | 401881.1223 | 241 |  | 179400 | 3000 | 584281.1223
Hours
[11 empty] | 24 | 144
L/Hour
Winter Conditions | [6 empty] | 90 | L | 15 | 6
|  | Schedule | 15 | Months
|  | Cost |  |  | Quantity | Sub Total | Total
United Rentals | Frost Fighters | 602 | month | 9.1 litres / hour | 1 | 602 | 9030
| Tarps (10) | 73 | ea |  | 1 | 73 | 1095
| Fans | 355 | month |  | 2 | 710 | 10650
| Fuel Cube | 609 | month |  | 1 | 609 | 9135
|  |  |  | Litres/day | Days |  | 0
| Fuel | 1.3 | litre | 144 | 0 | 0 | 0
| Delivery | 98 |  |  | 1 | 98 | 1470
| Pickup | 98 |  |  | 1 | 98 | 1470
Snow removal
[6 empty] | Total | 32850

## 2
0
[6 empty] | Existing Conditions |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
02 00 00 | Existing Conditions | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
02 41 00 | Demolition |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
02 82 00 | Asbestos Remediation | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
02 83 00 | Trenching | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
| Sanitary Trenching |  | ft | 65 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
| Conduit Trenching |  | ft | 35 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 2
0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0

## 3
0
[6 empty] | Concrete |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
03 11 00 | Concrete Forming | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
03 11 01 | Contractor Quote | [8 empty] | 0 | Spent incl Rebar | 561600
03 11 02.1 | Footings |  | ft | 25 | 0 |  | 0 | 0 | 302400 | 302400 | Optimal | 864000 | Can start within 2 weeks. Says 6 to 8 weeks of work left to do
03 11 02.2 | Walls |  | ft | 45 | 0 |  | 0 | 0 |  | 0
03 11 02.3 | Piers |  | ea | 150 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 302400
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
03 20 00 | Concrete Reinforcing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
03 20 01 | Contractor Quote | [8 empty] | 0 | [7 empty] | Type | Width |  | Height
03 20 02 | Rebar |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [8 empty] | A | B | D | Quantity | Volume m3
03 20 03 | Mesh |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | Footings | 1 |  |  |  |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [7 empty] | 2 |  |  |  |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [8 empty] | Length (FT) | Width (ft) | Height (ft)
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | Strip Footing | [5 empty] | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | Walls | [5 empty] | 0
[17 empty] | Piers | [5 empty] | 0
[9 empty] | Sub Total | 0 | [8 empty] | Area (SF) |  | Thickness (ft)
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [10 empty] | Slab - ground floor | [5 empty] | 0
03 30 00 | Cast-in-Place Concrete | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | [6 empty] | Slab - 2nd floor | [5 empty] | 0
03 30 01 | SOG Volume | 264.5133 | m3 | 181.42 | 47988.0079 |  | 0 | 0 |  | 47988.0079 | Spent | 100052.75 |  | 25MPA | 281.3335
| Structural Slab | 493.9534 | m3 | 210.58 | 104016.7088 |  | 0 | 0 |  | 104016.7088 | 2024 Prices |  |  | 30MPA | 22.9565
03 30 02 | Footing Volume | 16.8202 | m3 | 181.42 | 3051.5219 |  | 0 | 0 |  | 3051.5219 |  |  |  | 35MPA | 495.4485 |  | Exterior Pads | [5 empty] | 0
03 30 03 | Foundation Wall Volume | 22.9565 | m3 | 197.6 | 4536.198 |  | 0 | 0 |  | 4536.198
03 30 04 | Columns | 1.4951 | m3 | 210.58 | 314.8444 |  | 0 | 0 |  | 314.8444
| Retaining Walls | 35.8491 | m3 | 197.6 | 7083.7877 |  | 0 | 0 |  | 7083.7877
| Retaining Footings | 4.021 | m3 | 181.42 | 729.4884 |  | 0 | 0 |  | 729.4884
| Already Spent | [8 empty] | 0
| Pump Hrs | 23.9888 | Hrs | 280 | 6716.8693 |  | 0 | 0 |  | 6716.8693 | 38M Pump | [9 empty] | Total Volume - Slab |  | 0
03 30 04 | Pump | 839.6087 | m3 | 4 | 3358.4346 |  | 0 | 0 |  | 3358.4346 | [10 empty] | Total Volume - Footing |  | 0
[9 empty] | Sub Total | 177795.8609 | [10 empty] | Total Volume - Walls |  | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [14 empty] | Total Volume - Exterior |  | 0
03 35 00 | Concrete Finishing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Coating for garage slab
| Slab Finishing - Ground Floor | 34600 | sf | 2 |  |  | 0 | 0 | 44527 | 44527 | Texcon | 46000
| Slab Finishing - 2nd Floor | 0 | sf | 1 | 0 |  | 0 | 0 |  | 0 | Euro | 44527
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Champion | 51394
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 44527
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
03 40 00 | Precast Concrete | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 | 77850 | 77850 | APC | 77850
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 77850
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
03 60 00 | Foundation Materials | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
03 60 01 | Insulation | 340 | sheet | 26 | 8840 | 113.3333 | 60 | 6800 |  | 15640 | Labour Spent | 31200
03 60 02 | Vapour Barrier | 9 | rolls | 615 | 5535 | 45 | 60 | 2700 |  | 8235 | Materials Spent | 33171
| Foundation waterproofing allowance | 3680 | SF | 12 | 44160 |  | 0 | 0 |  | 44160
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 68035
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 3 | [14 empty] | M3
10.2239 |  |  |  |  | 236330.8609 | 158.3333 |  | 9500 | 424777 | 670607.8609 |  | 1 | F1 Footing | 284 | CF | 8.042
[12 empty] | 2 | F1 Wall | 737 | CF | 20.8695
[12 empty] | 3 | Footing B | 256 | CF | 7.2491
[12 empty] | 4 | Columns | 48 | CF | 1.3592
[12 empty] | 5 | SOG | 8492 | CF | 240.4667
[12 empty] | 6 | Structural Slab | 15858 | CF | 449.0486
[12 empty] | 7 | Retaining Walls | 1266 |  | 35.8491
[12 empty] | 8 | Retaining Footing | 142 |  | 4.021

## 4
0
[6 empty] | Masonry |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
04 20 00 | Unit Masonry | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  | Veneer | Interior Blocks | Ston Masonry | 131400 | Labour only for exterior. Labour + Mat for interior block walls
| Culture Stone | 3290 | SF | 50 |  |  | 0 | 0 | 104000 | 104000 | JP Masonry | 104000 | 36360
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Vintage (Late) | 219495
| Block Walls | 1600 | SF | 40 |  |  | 0 | 0 | 36360 | 36360
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Shaw Stone supply | 51352 | Screwed Vena Stone
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | AVT Install | 55000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 140360
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
04 43 00 | Stone Masonry | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 4
2.1399 |  |  |  |  | 0 | 0 |  | 0 | 140360 | 140360

## 5
0
[6 empty] | Metals |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
05 12 00 | Structural Steel Framing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 | 136100 | 136100 | Summit | 136100 | $4500 extra for brick lintels
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
| Brick Lintels |  | LS | 0 | 0 |  | 0 | 0 | 4500 | 4500
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
| Metal clips for handrails | 8 | LS | 100 | 800 |  | 0 | 0 |  | 800
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 141400
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
05 20 00 | Metal Joists | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
05 30 00 | Metal Decking | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
05 51 00 | Metal Stairs | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
05 52 00 | Metal Railings | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | ADS | 67400
|  | 59 | Unit | 1752.8814 |  |  | 0 | 0 | 73570 | 73570 | FCG | 73570
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[11 empty] | Joyce per unit | 1752.8814
[9 empty] | Sub Total | 73570
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
05 59 00 | Metal Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 5
3.2774 |  |  |  |  | 800 | 0 |  | 0 | 214170 | 214970

## 6
0
[6 empty] | Wood & Plastics |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
06 11 00 | Framing Labour | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
[7 empty] | 0 | 0 | 459330 | 459330 | AVT | 445000 | Framing Only. They supply manlift, we supply crane and zoom boom
| Allowance for corner columns install | 6 | LS | 500 | 3000 |  | 0 | 0 |  | 3000 | Big Bang | 545000 | Framing, strapping and tyvek install
[7 empty] | 0 | 0 |  | 0 | CMS | 459330 | Includes deck install and Windows install & Solar Panel Reinforcements
| Crane | 15 | wks | 7000 | 105000 |  | 0 | 0 |  | 105000 | Gbro | 569550 | Includes deck install and Windows install
| Crane Setup/Dismantle | 2 | LS | 2000 | 4000 |  | 0 | 0 |  | 4000 | East Coast | 395000 | Framing and concrete deck install. Additional $45k for window install
[7 empty] | 0 | 0 |  | 0 | S&J | 389956.2 | Includes deck install and Windows install
[7 empty] | 0 | 0 |  | 0 | Branco | 477627.2 | Includes deck install and Windows install & Solar Panel Reinforcements
[9 empty] | Sub Total | 571330
06 20 00 | Framing Materials | Qty | Unit | U. Price | Sub Total |  |  |  | Quote | Total
| Lumber & Fasterners Allowance | 59 | Unit | 3250 | 191750 |  |  |  |  | 191750 | Belle Foret per unit | 2791.1975 | Added $ for truss bracing
| 2x6 Stud |  | ft | 0.81 | 0 |  |  |  |  | 0
| 2x8 |  | ft | 1.24 | 0 |  |  |  |  | 0
| 2x10 |  | ft | 1.61 | 0 |  |  |  |  | 0
| 1x3 |  | ft | 0.25 | 0 |  |  |  |  | 0
| 1x4 |  | ft | 0.37 | 0 |  |  |  |  | 0 |  | Per Unit
| PLYWOOD | [8 empty] | 0 | Belle Foret Atlas | 21621.1746
| 1/2" Standard |  | EA | 30.65 | 0 |  |  |  |  | 0 | Joyce Atlas | 23077.9661
| 5/8" Standard |  | EA | 43.69 | 0 |  |  |  |  | 0
| 3/4" Standard |  | EA | 47.47 | 0 |  |  |  |  | 0 |  | Walls | Floors | Trusses | Stairs | Total |  | Additional with solar bracing
[11 empty] | Atlas | 466300 | 524850 | 104900 | 32400 | 1128450 | Total with Trusses | 19500
| Panel Allowance | 59 | EA | 23077.97 |  |  |  |  | 1070073.66 | 1070073.66 | T&M | 1003550 | Incl | Not Incl | Incl | 930650 | 1070073.66
Truss Peninsule
[11 empty] | Gable | Not Incl | 266240.78 | 139423.66 | Not Incl | Floor does not have boarding
[9 empty] | Sub Total | 1261823.66
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
06 22 00 | Millwork | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Extreme Kitchen
|  | 59 | Unit | 6000 |  |  | 0 | 0 | 425900 | 425900 | Foxwood | 425900 | Melamine Counter top and doors
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Royalty | 633000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Shaw
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Triangle | 446883.98 | Pricing quartz top with melamine doors
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Laforest | 604750 | Soft Close +$44,250. Quartz +$372,000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior (Late) | 404334.08
[9 empty] | Sub Total | 425900
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
06 41 00 | Architechtural Wood Casework | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
| Pre-Hung Doors | 59 | Unit | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
06 42 00 | Wood Paneling | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
06 43 00 | Wood Stairs and Railings | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[15 empty] | Trim LF | Suite QTY | Total Trim | Door Trim | Total Door Trim | Pre-hung Doors
[9 empty] | Sub Total | 0 |  |  |  | Suite A Floor Trim | 244 | 1 | 244 | 200 | 200 | 5 | 5
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [7 empty] | Suite B Floor Trim | 238 | 7 | 1666 | 240 | 1680 | 6 | 42
06 46 00 | Wood Trim | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total |  |  |  | Suite BF Trim | 231 | 3 | 693 | 240 | 720 | 6 | 18
| Floor Trim | 19179.6 | LF | 1.25 |  |  | 0 | 0 | 68450 | 68450 | GB Finish | 68450 |  | Suite C Floor Trim | 227 | 4 | 908 | 280 | 1120 | 7 | 28
| Door Trim | 19448 | LF | 1.03 |  |  | 0 | 0 |  | 0 | S&J | 92424.96 |  | Suite D Trim | 288 | 16 | 4608 | 240 | 3840 | 6 | 96
| Pre-hung doors | 442 | LS | 225 |  |  | 0 | 0 |  | 0 |  |  |  | Suite E Trim | 389 | 4 | 1556 | 400 | 1600 | 10 | 40
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | Suite F Trim | 353 | 12 | 4236 | 400 | 4800 | 10 | 120
|  | 59 | Unit | 4192.4389 | 247353.8944 |  | 0 | 0 |  | 247353.8944 | Belle Foret per Unit | 4192.4389 | Includes pre-hung doors | Suite G Trim | 236 | 1 | 236 | 240 | 240 | 6 | 6
[14 empty] | Suite H Trim | 343 | 7 | 2401 | 360 | 2520 | 9 | 63
[9 empty] | Sub Total | 315803.8944 |  |  |  | Suite I Trim | 222 | 4 | 888 | 240 | 960 | 6 | 24
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [9 empty] | 10% Factor | 1743.6 |  | 1768
06 48 00 | Wood Frames | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | [5 empty] | Total | 19179.6 |  | 19448 |  | 442
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 6
39.2557 |  |  |  |  | 551103.8944 | 0 |  | 0 | 2023753.66 | 2574857.5544

## 7
0
[6 empty] | Thermal & Moisture Protection |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
07 21 00 | Thermal Insulation | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
07 21 16 | Blanket Insulation | 59 | Unit | 3880.4407 |  |  | 0 | 0 | 237835 | 237835 | Mike's | 237835 | Alternative in floor insulation
07 21 26 | Blown Insulation |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Ghiro / BenJo | 193676 | Missing spray foam in underground garage
07 21 29 | Sprayed Insulation |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Trinity | 222009 | Blown insulation only
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[11 empty] | Joyce per unit | 3880.4407
[9 empty] | Sub Total | 237835
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 24 00 | Sound Proofing | Qty | Unit | U. Price | Sub Total | SF | U. Price | Sub Total | Quote | Total
| Acoustiboard | 59032.8 | SF | 2.88 | 170014.464 | 59032.8 | 1.5 | 88549.2 |  | 258563.664
| Sealant | 45 | Unit | 51.43 | 2314.35 | 45 | 240 | 10800 |  | 13114.35 | Assuming 1 tube can do 10'
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 271678.014
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [7 empty] | Previous Quote
07 31 00 | Shingles | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total |  |  |  | All Angles Covered | 87550
|  | 16398 | SF | 5.3031 | 81750 |  | 0 | 0 |  | 81750 | All Angles | 81750
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Belvue | 101990.13
[9 empty] | Sub Total | 81750 | Eastbound | 102450 |  | Joyce per sf/floor | 5.3031
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Maximum | 57500 | Install only
07 42 00 | Wall Panels | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 46 00 | Siding | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | Century
| Metal Siding | 24309 | SF | 12 | 291708 |  | 0 | 0 |  | 291708 | Shaw Materials | 192414.29
|  |  | LS | 0 | 0 |  | 0 | 0 | 270000 | 270000 | AVT Install | 325000 | $55k credit if no need to install brick veneer. Includes strapping install
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Century | 715000 | 29.413 | Price per sf
[9 empty] | Sub Total | 561708 | Riztcor Install | $550 Per square | $5.50 per SF | 133699.5
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 52 00 | Modified Bituminous Membrane Roofing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 53 00 | Elastomeric Membrane Roofing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 62 00 | Sheet Metal Flashing and Trim | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 63 00 | Sheet Metal Roofing Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 64 00 | Sheet Metal Wall Cladding | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 72 00 | Roof Accessories | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
07 72 26 | Ridge Vents |  | LS | 0 | 0 |  | 0 | 0 |  | 0
07 72 33 | Roof Hatches |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 81 00 | Applied Fireproofing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | Mike's | 26550
07 84 00 | Firestopping | 59 | Unit | 457.1429 |  |  | 0 | 0 | 26550 | 26550 | Premium | 48376 |  |  | Insulation
| Underground Garage Allowance |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Fundy | 21180
[11 empty] | Belle Foret per unit | 457.1429
[9 empty] | Sub Total | 26550 | Joyce per unit | 358.9831
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
07 90 00 | Joint Protection | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 7
0 |  |  |  |  | 545786.814 | 59077.8 |  | 99349.2 | 534385 | 1179521.014

## 8
0
[6 empty] | Openings |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
08 11 00 | Metal Doors and Frames | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
08 11 13 | Hollow Metal Doors and Frames | 59 | Unit | 2040.8644 |  |  | 0 | 0 | 89875 | 89875 | Sevy | 89875
08 11 16 | Aluminum Doors and Frames |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[11 empty] | Joyce | 2040.8644
[9 empty] | Sub Total | 89875
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 14 00 | Wood Doors | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 31 00 | Access Doors and Panels | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
| Attict Hatches | 1 | LS | 8000 | 8000 |  | 0 | 0 |  | 8000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 8000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 32 00 | Sliding Gates | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 33 00 | Coiling Doors and Drilles | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 | 10984.51 | 10984.51 | Gagnon | 10984.51
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Iller | 7273
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 10984.51
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 34 00 | Special Function Doors | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 38 00 | Traffic Doors | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 41 00 | Entrances and Storefronts | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  | 1 | LS | 35000 |  |  | 0 | 0 | 39425 | 39425 | FCG | 39425
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Royal | 50837
[9 empty] | Sub Total | 39425
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Economy | 38300
08 44 00 | Curtain Wall and Glazed Assemblies | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [5 empty] | Option 1 | Option 2
08 50 00 | Windows | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | Global | 127003.4 | 126145.3 | Option 1 is spec but does not meet NAFS. Option 2 offers alternative split window half operable. | W1A | 106
08 51 00 | Metal Windows |  | LS | 0 | 0 |  | 0 | 0 | 126145.3 | 126145.3 | Atlantic | 121656.5 | 120648.5 | Option 2 is fixed count. Balcony doors tempered | W1B | 16
08 52 00 | Wood Windows |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Maritime | 155674.41 | 133974.46 | Did not include BF unit doors | W1C | 17
08 53 00 | Plastic Windows | 59 | Unit | 5243.5793 |  |  | 0 | 0 |  | 0 | Ghiro | 146347.04 | 148591.52 | Option 2 is fixed count | W2A | 25
08 54 00 | Composite Windows |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | PatioA | 56
[9 empty] | Sub Total | 126145.3 | Joyce | 5243.5793 |  |  | PatioB | 3
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 70 00 | Hardware | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 81 00 | Glass Glazing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | Century
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | FCG
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 83 00 | Mirrors | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 87 00 | Glazing Surface Films | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
08 91 00 | Louvers | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 8
0 |  |  |  |  | 8000 | 0 |  | 0 | 266429.81 | 274429.81

## 9
0
[6 empty] | Finishes |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
09 20 00 | Plaster and Gypsum Board | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | SF | 0 | 0 |  | 0 | 0 | 1139222 | 1139222 | A1 | 1209800 | Price no longer valid - Merge with Arsenault | A1 | 1298700
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0 | Fundy | 1138510 | Frame bulkheads extra $28,640 | Cheaper when using with firestopping
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0 | Arsenault | 1139222 | Revised price
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 1139222
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
09 30 00 | Tiling | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
09 50 00 | Ceiling | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
09 60 00 | Flooring | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
09 61 00 | Concrete Floor Polishing | 17300 | SF | 7 | 121100 |  | 0 | 0 |  | 121100 | Need epoxy quotes | Expert Concrete
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
09 62 00 | Specialty Flooring |  | SF | 0 | 0 |  | 0 | 0 |  | 0
09 64 00 | Wood Flooring |  | SF | 0 | 0 |  | 0 | 0 |  | 0
09 65 00 | VCT |  | SF | 0 | 0 |  | 0 | 0 |  | 0 | Ritchies | 290000 | Meets Soprema Acoustiboard requirements.
09 67 00 | LVT | 65592 | SF | 4.5 |  |  | 0 | 0 | 290000 | 290000 | Floors Plus | 305400 | Revised to meeet Soprema requirements
09 68 00 | Carpet Tile |  | SF | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior (Late) | 240697.41
[9 empty] | Sub Total | 411100
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
09 72 00 | Wall Coverings | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
|  |  | SF | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
09 91 00 | Painting | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
09 91 13 | Exterior Painting |  | SF | 0 | 0 |  | 0 | 0 |  | 0 | Advantage | 200000
09 91 23 | Interior Painting |  | SF | 0 | 0 |  | 0 | 0 | 197003 | 197003 | D&S | 331537
[11 empty] | P4X | 218205
[11 empty] | PaintGenix | 197003
Priority
[9 empty] | Sub Total | 197003
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 9
#VALUE! |  |  |  |  | 121100 | 0 |  | 0 | 1626225 | 1747325

## 10
0
[6 empty] | Specalties |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
10 11 00 | Visual Display Units | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 14 00 | Signage | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
| Mailbox | 1 | LS | 5000 |  |  | 0 | 0 | 10950 | 10950 | Short | 10950
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 10950
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 20 00 | Interior Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
10 21 00 | Compartments and Cubicles |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Short
10 21 13 | Toilet Compartments |  | LS | 0 | 0 |  | 0 | 0 |  | 0
10 22 00 | Partitions |  | LS | 0 | 0 |  | 0 | 0 |  | 0
10 22 19 | Demountable Partitions |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior Chrome (Late) | 2296
10 22 39 | Mirror |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior Black (Late) | 3116
10 22 43 | Sliding Partions | 59 | Unit | 203.21 | 11989.39 |  | 60 | 0 |  | 11989.39 | Master Interior Mirror (Black) | 5904
10 28 00 | Toilet , Bath, and Laundry Accessories |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 11989.39
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 44 00 | Fire Protection Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
10 44 16 | Fire Extinguishers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 51 00 | Lockers | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 | 31062.37 | 31062.37 | Eastern | 36900
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Stor-it | 31062.37
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Maritime | 57000
[11 empty] | Groundtek | 52685
[9 empty] | Sub Total | 31062.37
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 57 00 | Wardrobe and Closet Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
| Wire shelving |  | LS | 0 | 0 |  | 0 | 0 | 32532 | 32532 | Hang It | 32532
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 32532
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
10 70 00 | Exterior Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
10 73 00 | Bike Rack | 1 | LS | 2000 | 1340 | 5 | 60 | 300 |  | 1640 | Eastern | 1340
10 73 16 | Canopies |  | LS | 0 | 0 |  | 0 | 0 |  | 0
10 75 00 | Flagpoles
[9 empty] | Sub Total | 1640
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 10
0 |  |  |  |  | 13329.39 | 5 |  | 300 | 74544.37 | 88173.76

## 11
0
[6 empty] | Equipment |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
11 11 00 | Vehicle Service Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 13 00 | Loading Dock Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 30 00 | Residential Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total |  |  |  | Previous Quote
11 30 13 | Residential Appliances | 59 | Unit | 3400 | 200600 |  | 0 | 0 |  | 200600 | Does not follow ID schedule |  |  | Greenfoot | 227543
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 200600
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 41 00 | Food Storage Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
11 41 23 | Walk-In Coolers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 48 00 | Food service Cleaning and Disposal Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
11 48 13 | Commercial Dishwasher |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 52 00 | Audio-Visual Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
11 53 00 | Laboratory Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 11
3.0583 |  |  |  |  | 200600 | 0 |  | 0 | 0 | 200600

## 12
0
[6 empty] | Furnishing |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
12 20 00 | Window Treatments | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
12 21 00 | Window Blinds | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  | 59 | Unit | 700 | 41300 |  | 0 | 0 |  | 41300 | Interior Visions
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 41300
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
12 30 00 | Casework | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
12 32 00 | Manufactured Wood Casework | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
12 35 00 | Specialty Casework | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
12 36 00 | Countertops | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 12
0.62965 |  |  |  |  | 41300 | 0 |  | 0 | 0 | 41300

## 13
0
[6 empty] | Special Construction |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
| Solar |  | LS | 0 | 0 |  | 0 | 0 | 86400 | 86400 | Trusun |  | Confirmed verbally with Alex Lissandro 19-Aug
| Framing |  | LS | 0 | 0 |  | 0 | 0 | 25000 | 25000 | Atlas, CMS, Materials
| Electrical |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Greenfoot | 86400 | Includes electrical portion of the work. Their estimated kw/h is 100 short.
| Contingency for Greenfoot | 1 | LS | 10000 | 10000 |  | 0 | 0 |  | 10000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 121400
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 13
1.8508 |  |  |  |  | 10000 | 0 |  | 0 | 111400 | 121400

## 14
0
[6 empty] | Conveying Equipment |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
14 20 00 | Elevators | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | Kone | 189000
|  |  | LS | 0 | 0 |  | 0 | 0 | 155285 | 155285 | Kone | 192000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Otis | 193980
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | TK | 155285 | Potential mods to pit required
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
14 40 00 | Lifts | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
14 42 00 | Wheelchair Lifts | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 14
0 |  |  |  |  | 0 | 0 |  | 0 | 155285 | 0

## 21
0
[6 empty] | Fire Suppression |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
21 10 00 | Water-Based Fire-Suppression System | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | B&G | 248500 | Wet system in parkade | B&G | 340700
|  |  | LS | 0 | 0 |  | 0 | 0 | 212000 | 212000 | Deploy | 252546.1 |  | Vipond | 236700
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Troy | 279000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Viking | 209800 | Mix of iron and CPVC piping. 4 Stories does not require dry system in attict
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Vipond | 221900 | All iron piping.
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Leblanc | 212000 | All iron piping.
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 212000
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 21
3.2321 |  |  |  |  | 0 | 0 |  | 0 | 212000 | 212000

## 22
0
[6 empty] | Plumbing |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
22 10 00 | Plumbing Piping | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  | 59 | Unit | 10779.661 |  |  | 0 | 0 |  | 0 | Spent | 17707
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Fixtures
|  |  | LS | 0 | 0 |  | 0 | 0 | 674850 | 674850 | JR Snowdon | 632530.34 | 195093.54
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Premiere | 674850 | Cannot start rough ins until March
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | Snowdon Comparison to Master
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior Fixtures Black | 35256 |  | 48743.96
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Master Interior Fixtures Partial Chrome | 32436
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Joyce | 10779.661
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 674850
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
22 30 00 | Plumbing Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
22 33 00 | Electric Domestic Water Heaters |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 34 00 | Fuel-Fired Domestic Water Heaters |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
22 40 00 | Plumbing Fixtures | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
22 42 00 | Commercial Plumbing Fixtures | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
22 42 13 | Commercial Water Closets, Urinals, and Bidets |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 13.13 | Commercial Water Closets |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 13.16 | Commercial Urinals |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 16 | Commercial Lavatories and Sinks |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 16.13 | Commercial Lavatories |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 16.16 | Commercial Sinks |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 19 | Commercial Bathtubs |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 23 | Commercial Showers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 26 | Commercial Disposers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 29 | Shampoo Bowls |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 33 | Wash Fountains |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 36 | Commercial Laundry Trays |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 39 | Commercial Faucets, Supplies, and Trim Flushometers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 42 43 | Flushometers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
22 45 00 | Emergency Plumbing Fixtures | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
22 45 13 | Emergency Showers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
22 45 16 | Eyewash Station |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
22 47 00 | Drinking Fountains and Water Coolers | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 22
10.2886 |  |  |  |  | 0 | 0 |  | 0 | 674850 | 674850

## 23
0
[6 empty] | HVAC |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
23 07 00 | HVAC Insulation | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Conair | 509800 | Alternative heat pumps | GreenFoot | 471000
|  | 59 | Unit | 7580.5085 |  |  | 0 | 0 | 467650 | 467650 | Greenfoot | 467650 | Alternative heat pumps Equivalet to Hisense. Removed in-unit professional balancing. | Ray Mutch | 337362 | HP and HRV Only. No Common Areas
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Sica | 539275
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | ECR | 686000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Coldtech | 545250
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[11 empty] | Joyce | 7580.5085
[9 empty] | Sub Total | 467650
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 08 00 | Commissioning of HVAC | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 09 00 | Instrumentation and Control for HVAC | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 11 00 | Facility Fuel piping | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
23 11 23 | Facility Natural Gas Piping |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 13 00 | Facility Fuel Storage | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 20 00 | HVAC Piping and Pumps | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 23 00 | Refrigerant Piping | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 30 00 | HVAC Air Distribution | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
23 31 00 | HVAC Ducts and Casings |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 31 12 | Metal Ducts |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 31 12.13 | Rectangular Metal Ducts |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 31 12.16 | Round and Flat-Oval Spiral Ducts |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 33 00 | Air Duct Accessories |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 33 46 | Flexible Ducts |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 34 00 | HVAC Fans |  | LS | 0 | 0 |  | 0 | 0 |  | 0
23 38 00 | Ventilation Hoods |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 70 00 | Central HVAC Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
23 74 00 | Packaged Outdoor HVAC Equipment |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 83 00 | Radiant Heating Units | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
23 84 00 | Humidity Control Equipment | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 23
7.1297 |  |  |  |  | 0 | 0 |  | 0 | 467650 | 467650

## 25
0
[6 empty] | Controls |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
25 00 00 | Integrated Automation | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 25
0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0

## 26
0
[6 empty] | Electrical |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
[11 empty] | sub | qty | units | unit $ | ext
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
26 09 00 | Instrumentation and Controls for Electrical Systems | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
26 09 13 | Electrical Contractor |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Amplify | 889500 | Solar Mods Included
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Lakeview | 1091500
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Lumar | 886000 | Solar Mods Included
|  | 59 | Unit | 13289.4068 |  |  | 0 | 0 | 770000 | 770000 | Melco | 770000 | $9,750 additional for Solar
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Total | 733500
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [7 empty] | Exterior |  | Large |  | Pendant |  | Small |  | Vanity
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | A | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 17 | 17 | 1 | 1
[11 empty] | Joyce | 13289.4068 |  |  |  | B | 7 | 1 | 7 | 1 | 7 | 3 | 21 | 13 | 91 | 1 | 7
[9 empty] | Sub Total | 770000 | [5 empty] | C | 4 | 1 | 4 | 1 | 4 | 3 | 12 | 14 | 56 | 1 | 4
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor | [9 empty] | D | 16 | 1 | 16 | 2 | 32 | 3 | 48 | 14 | 224 | 1 | 16
26 10 00 | Medium-Voltage Electrical Distribution | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total | [5 empty] | E | 4 | 1 | 4 | 3 | 12 | 3 | 12 | 20 | 80 | 2 | 8
26 11 00 | Solar Panels |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Trusun | 124241 | *** In Div 13 |  |  | F | 12 | 1 | 12 | 2 | 24 | 3 | 36 | 20 | 240 | 2 | 24
26 12 00 | Electrical Change |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | G | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 13 | 13 | 1 | 1
26 13 00 | Structural Change |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | H | 7 | 1 | 7 | 2 | 14 | 3 | 21 | 19 | 133 | 2 | 14
26 16 00 | Medium-Voltage Metering |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | I | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 15 | 60 | 1 | 4
26 18 00 | Medium-Voltage Circuit Protection Devices |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | BF | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 16 | 48 | 1 | 3
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | Total |  |  | 59 |  | 102 |  | 163 |  | 962 |  | 82
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
26 50 00 | Lighting | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
26 51 00 | Exterior Light | 59 | LS | 80 | 4720 |  | 0 | 0 |  | 4720 | Master Interior
26 52 00 | Large Flush | 102 | LS | 42 | 4284 |  | 0 | 0 |  | 4284 | Master Interior
26 56 00 | Pendant | 163 | LS | 89 | 14507 |  | 0 | 0 |  | 14507 | Master Interior
| Small Flush | 962 | LS | 21 | 20202 |  | 0 | 0 |  | 20202 | Master Interior
| Vanity | 82 | LS | 112 | 9184 |  | 0 | 0 |  | 9184 | Master Interior
[9 empty] | Sub Total | 52897
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 26
12.5457 |  |  |  |  | 52897 | 0 |  | 0 | 770000 | 822897

## 27
0
[6 empty] | Communications |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
27 10 00 | Structured Cabling | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
27 20 00 | Data Communications | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
27 21 00 | Data Communications Network Equipment |  | LS | 0 | 0 |  | 0 | 0 |  | 0
27 22 00 | Data Communications Hardware |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
27 30 00 | Voice Communications | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
27 40 00 | Audio-Voice Communications | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
27 50 00 | Distributed Communications and Monitoring Systems | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 27
0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0

## 28
0
[6 empty] | Security |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
28 10 00 | Access Control | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
28 15 00 | Access Control Hardware Devices |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
28 20 00 | Video Surveillance | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
28 30 00 | Security Detection, Aarm, and Monitoring | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
28 40 00 | Life Safety | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
28 46 00 | Fire Detection and Alarm |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 28
0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0

## 31
0
[6 empty] | Earthwork |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
31 10 00 | Site Clearing | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
31 10 00 | Site Clearing |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 11 00 | Clearing and Grubbing |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
31 20 00 | Earth Moving | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
31 22 00 | Grading |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 22 13 | Rough Grading |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Spent | 500000
31 22 16 | Fine Grading |  | LS | 0 | 0 |  | 0 | 0 | 228300 | 228300 | Delway Original | 728300 | *** Not confirmed
31 23 00 | Excavation and Fill |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | 506-627-6727 | Devin | Need plumber to do underground
31 23 13 | Subgrade Preparation |  | LS | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Need to know if the city is doing the tie in
31 23 16 | Allowance for Road Connection | 1 | LS | 40000 | 40000 |  | 0 | 0 |  | 40000 |  |  | Sent drawings for review
31 23 16.13 | Trenching |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 16.16 | Structural Excavation for Minor Structures |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 16.26 | Rock Removal |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 19 | Dewatering |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 23 | Fill |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 23.13 | Backfill |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 23.23 | Compaction |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 23.33 | Flowable Fill |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 23.43 | Geofoam |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 23 33 | Trenching and Backfilling |  | LS | 0 | 0 |  | 0 | 0 |  | 0
31 25 00 | Erosion nd Sedimentation Controls |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 268300
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
31 37 00 | Riprap | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
31 70 00 | Tunneling | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 31
4.0904 |  |  |  |  | 40000 | 0 |  | 0 | 228300 | 268300

## 32
0
[6 empty] | Exterior Improvements |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info | Previous Quotes
32 10 00 | Bases, Ballasts, and Paving | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
32 11 00 | Base Course |  | LS | 0 | 0 |  | 0 | 0 | 53250 | 53250 | MacArthurs | 53250 |  | Sewell | 64500
32 12 00 | Flexible Paving |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Modern |  | $43/m3
32 14 00 | Unit Paving |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Dexter | 87000
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 53250
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
32 16 00 | Curbs, Gutters, Sidewalks, and Driveways | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
32 16 13 | Curbs and Gutters |  | LS | 0 | 0 |  | 0 | 0 | 28809.84 | 28809.84
32 16 13.13 | Cast-In-Place Concrete Curbs and Gutters |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Reitzel | 28809.84
32 16 13.16 | Steel Faced Curbs |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Branco | 40380
32 16 13.23 | Precast Concrete Curbs and Gutters |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Bastech
32 16 13.33 | Asphalt Curbs |  | LS | 0 | 0 |  | 0 | 0 |  | 0
32 16 13.43 | Stone Curbs |  | LS | 0 | 0 |  | 0 | 0 |  | 0
32 16 23 | Sidewalks |  | LS | 0 | 0 |  | 0 | 0 |  | 0
32 16 33 | Driveways |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 28809.84
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
32 17 00 | Paving Specialties | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
32 17 13 | Parking Bumpers |  | LS | 0 | 0 |  | 0 | 0 |  | 0
32 17 23 | Pavement Markings |  | LS | 0 | 0 |  | 0 | 0 | 960 | 960 | Everline | 960
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 960
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
32 30 00 | Site Improvements | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
32 31 00 | Fences and Gates | 363 | LF | 115 |  |  | 0 | 0 |  | 0
32 32 00 | Bollards |  | LS | 0 | 0 |  | 0 | 0 | 16800 | 16800 | Eastern Bollards | 16800
32 33 00 | Site Furnishing |  | LS | 0 | 0 |  | 0 | 0 |  | 0
32 33 23 | Site Trash and Litter Receptacles |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 16800
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
32 90 00 | Planting | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
32 91 00 | Planting Preparation |  | LS | 0 | 0 |  | 0 | 0 | 51251.17 | 51251.17 | Reitzel | 51251.17
32 92 00 | Turf and Grasses |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Ayles | 51662.6
32 93 00 | Plants |  | LS | 0 | 0 |  | 0 | 0 |  | 0 | Branco | 56660
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 51251.17
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
|  | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 32
2.3032 |  |  |  |  | 0 | 0 |  | 0 | 151071.01 | 151071.01

## 33
0
[6 empty] | Utilities |  |  | Schedule
|  |  | Area: | 65592 | Sq. Ft. |  |  |  | 60 | Weeks
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor |  |  |  |  | Sub Contractor | Quote Total | Additional Quote Info
33 10 00 | Water Utilities | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
33 11 00 | Groundwater Sources |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 14 00 | Water Utility Transmission and Distribution |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
33 30 00 | Sanitary Sewerage | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
33 31 00 | Sanitary Sewerage Piping |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 32 00 | Sanitary Sewerage Equipment |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
33 40 00 | Stormwater Utilities | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
33 41 00 | Subdrainage |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 41 13 | Foundation Drainage |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 42 00 | Stormwater Conveyance |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 46 00 | Stormwater Management |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
CODE | DESCRIPTION | Materials & Equipment |  |  |  | Labor
33 70 00 | Electrical Utilities | Qty | Unit | U. Price | Sub Total | MHrs | U. Price | Sub Total | Quote | Total
33 71 00 | Electrical Utilities Transmission and Distribution |  | LS | 0 | 0 |  | 0 | 0 |  | 0
33 71 19 | Electrical Underground Ducts, Ductbanks, and Manholes |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
|  |  | LS | 0 | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub Total | 0
[5 empty] | Material Total | Total Hours |  | Labor Total | Contractor Total | TOTAL
$ / Sq.Ft | TOTAL DIVISION 33
0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0